## Arkusz1
TASK | Who | September |  |  |  | October |  |  |  | November |  |  |  | December |  |  |  | January
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Webpage
Newsletter AGENT | Damian | bar: September 1 to September 2
Calendar Agent | Damian | bar: September 1 to September 2
Content creating suppling | Organic (we), Experts, Ext. Companies (Olimp, OctoSello) | bar: September 1 to September 4
Managing content creating process | Dominika | bar: September 1 to September 4
Community Organistaion
Platform (Circle) | Tested, procedure | bar: September 1 to September 2
Community Bulding Organic | Marcin, Damian - networking , CH, SASU Sales team | bar: September 3 to October 4
Comminity Manager | Dominika | bar: September 3 to October 4
Community Bulding Paid | bar: November 1 to December 4
Selling of Membership
Organic Selling | bar: November 1 to December 4
Budget | Cost | September | October | November | December | 2025 | January | Feburary | March | April | May | June | July | August | September | October | November | December | 2026
COST
Project And Community Manager | 7.8638 | 629.108 | 629.108 | 629.108 | 629.108 | 2516.4319 | 629.108 | 629.108 | 629.108 | 1258.216 | 1258.216 | 1258.216 | 1258.216 | 1258.216 | 1258.216 | 1258.216 | 1258.216 | 1258.216 | 13211.2676
Qualified Management Costs |  | 550 | 550 | 550 | 550 |  | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 550 | 6600
Tooling
Circle | 173 | 173 | 173 | 173 | 173 | 692 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 173 | 2076
Serwer |  |  |  |  | 200 | 200 | [12 empty] | 0
CRM |  |  | 25 | 25 | 25 | 75 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 25 | 300
Zoom PRO
Paid Community Bulding |  |  |  | 500 | 500 | 1000 | 500 |  | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 500 | 5500
0
|  | 1352.108 | 1377.108 | 1877.108 | 2077.108 | 6683.4319 | 1877.108 | 1377.108 | 1877.108 | 2506.216 | 2506.216 | 2506.216 | 2506.216 | 2506.216 | 2506.216 | 2506.216 | 2506.216 | 2506.216 | 27687.2676
Income
Package GOLD | 5000 |  |  |  |  | 0 | January: 5000; March: 5000; May: 5000; September: 5000; November: 5000 | 25000
Package Silver | 1500 |  |  |  |  | 0 | 1500 | 1500 | 1500 | 1500 | 1500 | 1500 |  | 1500 | 1500 | 1500 | 1500 |  | 15000
Membership | 900 |  |  |  |  | 0 | 1800 | 1800 | 1800 | 1800 | 1800 | 1800 |  | 1800 | 1800 | 1800 | 1800 |  | 18000
Community | 60 |  |  |  |  | 0 | [12 empty] | 58000
[6 empty] | -6683.4319 | December: Profit | 30312.7324

## Management Costs
Qualified Costs of Management | Cost | Comment
Article Writing Marcin and Damian Costs | 30 | Hour
Webinar Conducting Marcin and Damian | 30 | Hour
Specific Projects (Events organised on Association Behalf)
Travel Expenses for internal project meetings
Internal Employee Costs both Damian amd Marcn | 10 | Hour
Website Maintance | 40